## Escenarios
Scenary N° | Information | YES / NO | Validacion checklist | Expected Result | Ejecutado S/N | Estate | Observations | JIRA
1
2

## SCENARIOS API (BE)
NRO | FEATURE | TYPE | TECHNIQUE | TEST SUMMARY | EXPECTED RESULT | STATUS | ACTUAL RESULT | TICKET BUGS
1 | User Authentication | Acceptance | Decission Table | Verify user authenticate with valid credentials | User should be authenticated with valid message | PASSED | User is autheticate and the server response is with status 200 ok
2 |  | Acceptance | Decission Table | Verify error message for invalid credentials | User should get an error message | PASSED | User is not authenticated and got 401 unauthorized
3 |  | Acceptance |  | Test token generation and expiration
4
5
6
7
8
9
10
11
12
13
14
15
16 | PRODUCT MANAGEMENT | API Testing | CRUD | Create a Product with POST method | A product should be created with status 201 ok | PASSED | A Product has been created with 201 status code
17 |  |  |  | Read Product list with GET method | A product should be listed with status 200 ok | PASSED | A Product list has been displyed with 200 status code
18 |  |  |  | Read a specific Product with GET method | A specific product by id should be listed with status 200 ok | PASSED | A specific product has been displyed with 200 status code
19 |  |  |  | Edit a Product with PUT method | A product should be updated with status 204 ok | PASSED | A specific product has been updated with 204 status code
20 |  |  |  | Delete a Product with DELETE method | A product should be deleted with status 204 ok no content | PASSED | A specific product has been updated with 204 status code
21 |  |  |  | Verify error handling for invalid product data | An error handling formatted and detailed should be displayed for invalid product data | FAILED | An incompleted error handling has been displayed | 100
22 |  |  |  | Test search and filter functionalities.
23
24
25
26
27 | ORDER PROCESSING |  |  | Create an order and verify order details. | An order should be created with order details | PASSED | An order has been created with order details
28 |  |  |  | Test order cancellation and status updates. | An order cancellation and status updates should be executed | PASSED | An order cancellation and status updates has been executed
29 |  |  |  | Verify error handling for invalid order operations. | An error handling for invalid order operations should be displayed. | PASSED | An error handling for invalid order operations has been displayed.

## SCENARIOS UI (FE)
NRO | FEATURE | TYPE | TECHNIQUE | TEST SUMMARY | EXPECTED RESULT | STATUS | ACTUAL RESULT | EVIDENCE | TICKET BUG
1 | User Authentication & Dashboard | Acceptance | Decission Table | Verify login functionalities in UI | User should be authenticated with valid message | PASSED | User is autheticate and thre is a confirmation message displayed
|  | Acceptance | Decission Table | Verify logout functionalities in UI | User should be able to logout from the wep app | FAILED | User unable to log out from web app |  | 101
2 |  | Acceptance | Decission Table | Test user dashboard data display and refresh | User dashboard data should be displayed and refreshed | FAILED | User dashboard data page is not displayed and refreshed |  | 102
4 |  | Negative |  | Verify to Do not access any web app page without a User is logged | nobody should be able to have access to the any web app | FAILED | Any user can access to anotehr web app
5 |  | Negative |  | Verify to access to homepage dashboard page after an user is logged | An User should be directed to the dashobard page | FAILED | The user is redirected to the same login page
6 |  | Acceptance |  | Verify Login Layout adapts on differents Devides | Website layout should be adapted correctly to various screen sizes | PASSED | Website layout is adapted correctly to various screen sizes
|  | Acceptance |  | Verify Login form layout is appropriately visible with width=1024 px | Login form layout should be displayed appropriately with width=1024 px | FAILED | Login and password text field dont have the complete drawn box fields
|  | Acceptance |  | Verify Keyboard Accessibility | All interactive elements should be reachable and operable | PASSED | All interactive elements are reachable and operable
|  | Acceptance |  | Verify Color Contrast and friendly page | Visual elements should be located in a user-friendly with consistent sizes between fields or buttons. | FAILED | Visual elements are not located in a user-friendly with consistent sizes between fields or buttons.
|  | Acceptance |  | Verify that error messages are accessible and provide clear feedback | They should be associated with the relevant form fields and provide actionable feedback | FAILED | Error messages do not provide clear feedback
7
8
9
27 | Product Listing & Order Processing | Acceptance |  | Verify product listing display | Product listing should be displayed | PASSED | Product listing is displayed
|  | Acceptance |  | Verify product listing filter | Product listing should be filtered | FAILED | Product listing is not filtered
28 |  | Acceptance |  | Test order creation, update, and cancellation workflows | Order creation, update, and cancellation workflows should work. | FAILED | Order creation, update, and cancellation workflows are not displayed.
|  | Acceptance |  | Verify Product Listing Layout adapts correctly to various screen sizes | Product Listing layout should be adapted correctly to various screen sizes | PASSED | Product Listing layout is adapted correctly to various screen sizes
|  | Acceptance |  | Verify Keyboard Accessibility | All interactive elements should be reachable and operable | PASSED | All interactive elements are reachable and operable
|  | Acceptance |  | Verify Color Contrast and friendly page | Visual elements should be located in a user-friendly with consistent sizes between fields or buttons. | FAILED | Visual elements are not located in a user-friendly with consistent sizes between fields or buttons.
|  | Acceptance |  | Verify that error messages are accessible and provide clear feedback | They should be associated with the relevant form fields and provide actionable feedback | FAILED | Error messages do not provide clear feedback when there are not products

## Usuario.
TEST PLAN
Type of Test: Funcionales
Made by:
Sprint N°
Evidence:
Observaciones: [aqui se sugiere por ejemplo que podamos escribir los pasos para llegar a la pantalla que estamos probando ]
Cliente: |  |  | Proyecto:
ITEM | Caso gral | Descripción del caso. | Pasos a seguir | Resultado Esperado | Ejecutado S/N | Estado | Observaciones | Ticket JIRA ID
1 | Admin
2 | New user
3 | New user
4 | New user
5 | New user
6 | New user
7 | New user
8 | New user
9 | New user
10 | New user
11 | New user
12 | New user
13 | New user
14 | menu ...
15 | menu ...
16 | menu ...
17 | menu ...
18
19 | menu ...
20 | menu ...
21 | Investment
1
2
3
4
5
6
7
8
9

## Login
TEST PLAN
Type of Tests: Funcionales
Made by:
Sprint N°
Evidence:
Observations: [aqui se sugiere por ejemplo que podamos escribir los pasos para llegar a la pantalla que estamos probando ]
Client: |  |  | Proyect:
ITEM | Caso gral | Descripción del caso. | Pasos a seguir | Resultado Esperado | Ejecutado S/N | Estado | Observaciones | Ticket JIRA ID
1 | Login
2 | Login
3 | Login
4 | Login
5 | Login
6 | Login
7 | Login
8 | Login
9 | Password
10 | New user
11 | New user
12 | New user
13 | New user
14 | menu ...
15 | menu ...
16 | menu ...
17 | menu ...
18
19 | menu ...
20 | menu ...
21 | Investment

## Decission table
| Conditions | Rule1 | Rule2 | Rule3 | Rule4
| UserName | F | T | F | T
| Password | F | F | T | T
| Output (E/V) | E | E | E | V
Legend : T: valid input
Legend : F: invalid input
Legend : E: Error message is invalid
Legend : V: valid Message is displayed

## BUGS
Nro | TITLE | DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | ACTUAL RESULT | ATTACHMENTS
100 | Incomplete error handling due to invalid product data in bode response | when the user tries to search a product by id product un swggaer or postman tool then in bode response show incomplete message code status | 1.- Authenticate in postman or swagger http://localhost:5044/swagger/index.html 2.- execute the get method by invalid id example "5" 3.- Watch the incomplete message in body response in postman or in the image in attachment seccion | Low | Incomplete error message is displayed not giving a properly feedback
101 | User unable to log out from web app | when a user wants to log out from the web app then is not possible | 1.- Go to http://localhost:3000/login and be logged 2.- Watch the log out doesnt exist in any page from the app | High | Log out tab doesn´t exist in the web app
102 | User dashboard data page is not displayed and refreshed | When a user wants to watch his information then dashboard user page is not refreshed | 1.- Go to http://localhost:3000/login and be logged 2.- Click on the dashboard tab 3.- Notice the information is not displayed and refreshed with new data | High | On the dashboard user page, this informative message “Welcome to the user dashboard!” is permanently displayed.